## GTM worksheet
GTM planning worksheet
From "Go-to-market strategy for B2B software companies" — marketingwithjay.uk/tools/go-to-market-strategy-b2b-software
Decision | What to answer | Your answer | Owner | Due date | Status
Primary ICP and segment | Industry, size, geography, technology environment, maturity and urgency of the companies you will target first.
Core buyer problem | The problem your software solves, in the buyer's words, and what happens if it stays unsolved.
Buying trigger | The event that starts a buying process: growth, a failed system, a regulation, a new leader.
Main alternative | What buyers use today instead: a competitor, a spreadsheet, an internal tool, doing nothing.
Differentiated value | Why a buyer should choose you over that alternative.
Evidence and proof | Demos, approved customer examples, data or references that support the claim.
GTM motion | Sales-led, product-led, partner-led or hybrid, and why it fits how buyers evaluate.
Primary channels | The few channels where your buyers research and engage, each with a defined role.
Main conversion action | Demo, trial, consultation or contact: the one action the plan drives towards.
Success metrics | A small set tied to the objective: qualified pipeline, demo-to-opportunity, activation.
Owners and milestones | Who owns each part of the plan and the dates that matter.
MWJ · marketingwithjay.uk · B2B marketing for tech, IT and software companies

## 90-day plan
90-day execution plan
Illustrative sequence — adapt to the product's readiness and your sales cycle.
Phase | Days | Task | Owner | Due date | Status
Validate | 1–30 | Confirm the ICP and priority segments
Validate | 1–30 | Map the buying committee and its evidence needs
Validate | 1–30 | Review competitors and current alternatives
Validate | 1–30 | Draft positioning and test it with customers or prospects
Validate | 1–30 | Agree success metrics and baselines
Prepare | 31–60 | Finalise website and campaign messaging
Prepare | 31–60 | Build priority assets: pages, decks, one pagers, demo
Prepare | 31–60 | Brief sales and partners; agree lead routing and follow-up
Prepare | 31–60 | Set up measurement and test conversion paths
Activate and learn | 61–90 | Launch the selected channels
Activate and learn | 61–90 | Monitor qualified responses and target-account engagement
Activate and learn | 61–90 | Review sales feedback and refine messaging
Activate and learn | 61–90 | Reallocate effort to what is working; document lessons
MWJ · marketingwithjay.uk · B2B marketing for tech, IT and software companies